MANAGEMENT OF CHANGE REQUEST

MOC-2026-0087  |  Upgrade of Mechanical Seal Arrangement, P-2104A/B

| MOC Number | MOC-2026-0087 | Date raised | 2026-09-01 |
| --- | --- | --- | --- |
| Change type | Permanent - Engineering / Hardware | Risk rank | Medium |
| Unit | CDU-2 - Crude Distillation Unit - 2 | Equipment | P-2104A / P-2104B |
| Originator | S. Pai | Current status | Pending Technical Review |
| Target completion | 2026-10-15 | Arising from | INC-2026-0042 |

## 1. Reason for change

Corrective action CAPA-0042-1 arising from incident INC-2026-0042 dated 2026-08-29.

## 2. Existing arrangement

API 682 Category 1, Arrangement 1 (single unpressurised) cartridge seal with API Plan 52 external reservoir. Seal kit part SK-682-2104.

## 3. Proposed arrangement

API 682 Category 2, Arrangement 3 (dual pressurised) cartridge seal with API Plan 53B bladder accumulator barrier fluid system. Seal kit part SK-682-2104-A3.

## 4. Technical justification

RCO service at 345 degC with a flash point below the operating temperature; a leak path to atmosphere is a Tier 2 process safety risk.

Arrangement 3 contains any inboard face failure within the barrier fluid, converting a loss of containment into an alarm.

Plan 53B removes the operator-dependent reservoir top-up that was a contributing factor in INC-2026-0042.

## 5. Impact assessment

| Discipline | Impact |
| --- | --- |
| Process | No change to process conditions or unit yields. |
| Piping | Removal of Plan 52 reservoir piping; new 53B accumulator skid, 0.9 m x 0.6 m footprint, at grade adjacent to pump. |
| Electrical | New level and pressure transmitters, 2 x 4-20 mA loops to DCS. Two new DCS alarm points required. |
| SOP | SOP-CDU2-014 requires revision (Rev 5) for barrier fluid pre-start checks. |
| Training | 2 hour refresher for all CDU-2 shift personnel before commissioning. |
| Cost | Estimated INR 34.6 lakh for both pumps including spares. |

## 6. Constraint on execution

Long lead item: seal kit SK-682-2104-A3 shows zero stock against a minimum of 2. Vendor lead time is 45 days. See SPR-ROT-001.

Consequently the earliest realistic execution date is governed by material availability rather than by engineering approval. The 45 day vendor lead time on seal kit SK-682-2104-A3 means that even with immediate approval and a purchase order placed on 2026-09-01, material would not be on site before mid October 2026. The target completion date of 2026-10-15 should be regarded as at risk.

## 7. Safety review comment

N. Bhat (Safety Officer), 2026-09-03: Concur with the upgrade. Note that Safety Circular SC-2026-11 restricts hot work in this area until 2026-11-30; the accumulator skid tie-in must therefore be scheduled inside the CDU-2 planned shutdown window or a separate deviation must be approved.

## 8. Pre-commissioning requirements

| No. | Requirement | Responsible |
| --- | --- | --- |
| 1 | Revise SOP-CDU2-014 to Rev 5 covering barrier fluid pre-start checks and the 0.05 mm alignment tolerance record. | A. Fernandes |
| 2 | Configure two new DCS alarm points for barrier fluid level low and barrier fluid pressure low. | Instrumentation |
| 3 | Complete 2 hour refresher for all CDU-2 shift personnel. | A. Fernandes |
| 4 | Update the P&ID PID-CDU2-003 and the equipment data sheet to reflect the Plan 53B system. | Engineering |
| 5 | Add barrier fluid level to the operator shift round check sheet (also required by CAPA-0042-3). | M. Shetty |
| 6 | Obtain hot work deviation permit or schedule tie-in inside the planned shutdown window, per SC-2026-11. | K. Rao |

## 9. Approval route

| Stage | Name | Date | Status |
| --- | --- | --- | --- |
| Originator | S. Pai | 2026-09-01 | Signed |
| Reviewer - Process | P. D'Souza | 2026-09-02 | Signed |
| Reviewer - Safety (HAZOP screening) | N. Bhat | 2026-09-03 | Signed with comment |
| Reviewer - Inspection | V. Nayak |  | Pending |
| Approver - DGM Operations | A. Fernandes |  | Pending |

This change shall not be executed until all approval stages above show Signed and the material availability constraint in Section 6 is resolved.